## Guide
CertiMinds ¦ Internal
Daily updates, mentor meeting minutes and weekly progress reports, in one file.
Full name | Abdalwahab Eltahir
Start date | 2026-10-11
Enter the Sunday of the first week, e.g. 27/09/2026
HOW TO USE
Daily Log | Each day you work, before you log off: type the date, then 3 to 5 short bullet points on what you achieved, your plan for tomorrow, and three quick ratings.
Meeting Minutes | Add one row after each mentor meeting.
Weekly Report | Complete one row at the end of each week. Keep it brief, a few lines per box is enough.
Ratings | All ratings are out of 5, where 1 = lowest and 5 = highest.
Colours | Yellow cells are for typing. Grey cells fill in by themselves.

## Daily Log
Daily Achievements Log
Associate: Abdalwahab Eltahir
One row for each day you work. Type the date first (Week and Day fill in by themselves), then 3 to 5 short bullet points. Press Alt+Enter for a new line inside a cell.
|  |  | DAILY UPDATE (short bullet points) |  | DAILY RATINGS (1 = lowest, 5 = highest)
Week | Date | Day | Today's Achievements | Plan for Tomorrow | Productivity today | How challenging was today | How much new was learned
2 | 2026-10-15 | Thu | Reviewed the Restaurant Management System demo. Made progress with Coursera coursework. Progressed with coursera courses. | Continue Coursera coursework . Implemente Payment Gateway. Progressed with coursera courses | 5 | 2 | 5
3 | 2026-10-18 | Sun | Payment Gateway implemented. Rewards redmption system implemented. User interface update. Progressed with coursera courses. | Continue Coursera coursework. improve the Restaurant Management System and UI. Improve my communication | 5 | 3 | 5
3 | 2026-10-19 | Mon | Finished implementing the Restaurant Management System. Tested the system to ensure its functionality works correctly. Documented the system’s features and functionalities. | Improve the user interface (UI) to make the system more user-friendly and visually appealing. Research additional features that could be implemented in the Restaurant Management System. Start working on implementing the selected new features and improvements. | 5 | 2 | 5
3 | 2026-10-20 | Tue | Researched UI/UX improvements. Evaluated new feature ideas. Advanced progress on Coursera coursework. | Finish implementing and styling the selected UI updates for the Restaurant Management System. Continue advancing through Coursera coursework modules. | 4 | 1 | 4

## Meeting Minutes
Mentor Meeting Minutes
Associate: Abdalwahab Eltahir
One row per mentor meeting.
ASSOCIATE FEEDBACK (1 = lowest, 5 = highest)
Date | Attendees | Progress Discussed | Demo Shown | Blockers Raised | Overall satisfaction (course & experience) | How challenging was it | How much new was learned | Action Items
2026-10-05 | Dr. Moad Idrissi, Dr. Ealius Azam and Abdalwahab Eltahir | looking into full stack development | No demo | None | 5 | 1 | 5 | Start with Coursera courses
2026-10-07 | Dr. Moad Idrissi, Dr. Ealius Azam and Abdalwahab Eltahir | Discussed Coursera progress, effective note taking practices, and strategies for using LLMs efficiently to reduce credit/token usage. Also discussed ways to improve confidence and communication skills | No demo | Communication skills and building confidence when communicating | 5 | 1 | 5 | Catch up on the current Coursera courses,Prepare to start the next Coursera course and working to improve my communication
2026-10-12 | Dr. Moad Idrissi, Dr. Ealius Azam and Abdalwahab Eltahir | Discussed Coursera progress, communication tips, lessons learned from the courses, | No demo | Some communication adjustments | 5 | 1 | 5 | Abdalwahab to develop a restaurant management system that utilizes chatbots and handles restaurant staff and management operations with a rewards system by Wednesday
2026-10-14 | Dr. Moad Idrissi, Dr. Ealius Azam and Abdalwahab Eltahir | Discussed progress on the Restaurant Management System, focusing on the Spring Boot backend and implemented features | Presented a demo of the Restaurant Management System to demonstrate the current implementation and progress. | None | 5 | 1 | 5 | Improve the UI and overall user experience, upload the latest project code to GitHub, and implement the remaining missing features in the Restaurant Management System.
Note on A5: Date of the mentor meeting.
Note on B5: Who attended, e.g. associate, mentor, Moad.
Note on C5: What progress was reviewed since the last meeting.
Note on D5: Any work the associate demonstrated, e.g. a feature, app or code walkthrough.
Note on E5: Anything stopping the associate from moving forward.
Note on I5: The tasks agreed in the meeting: what needs to be done, who will do it, and by when. Example: Irfan to finish the login page by Thursday.

## Weekly Report
Weekly Progress Report
Associate: Abdalwahab Eltahir
One row per week. Keep it brief, a few lines per box is enough.
WEEKLY RATINGS (out of 5)
Week | Week Ending | Technical Growth | Overall Adaptability | 1. What Was Covered | 2. Key Learning Points | 3. Challenges Faced | 4. Next Steps
1 | 2026-10-15 | 5 | 4 | Reviewed Coursera progress, communication skills, and the Restaurant Management System demo and Spring Boot backend. | Learned communication techniques and ways to improve backend development and user experience. | Identified communication improvement areas, UI issues, and incomplete system features. | Improve the UI, complete missing features, push code to GitHub, and develop chatbot, staff management, and rewards functionality by Wednesday.
2 | 2026-10-22
3 | 2026-10-29
4 | 2026-11-05
5 | 2026-11-12
6 | 2026-11-19
7 | 2026-11-26
8 | 2026-12-03
9 | 2026-12-10
10 | 2026-12-17
11 | 2026-12-24
12 | 2026-12-31
Technical Growth: 1 = no growth, 5 = significant growth. Overall Adaptability: 1 = struggled to adapt, 5 = picked up quickly, independently.
Note on B5: Calculated from the start date on the Guide tab (Thursday of each week).
Note on C5: 1 = no growth 5 = significant growth
Note on D5: 1 = struggled to adapt 5 = picked up quickly, independently
Note on E5: A short summary of what you worked on during the week.
Note on F5: What actually landed: the things worth remembering.
Note on G5: Where you got stuck, and how you handled it.
Note on H5: What you plan to focus on the following week.